## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone | 2016-12-15
Features in scope | use media player | developed a web page which uses the player to play back a video from media services | for a start have the video sitting in a folder | encoded the video
Features implemented | yes | yes | yes | yes
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #2
Date of milestone | 2017-02-07
Features in scope | build an ASP.Net MVC application which allows users to register/login maybe with social media account. | Code first approach to manage database | upload the video dynamically | UML class Diagram and relationships
Features in deficit this Iteration | still in progress | still in progress, managed an Insert | missing in this iteration
Iteration Comments & Summary |  | a lot of difficulties managing 2 FK | still investigating | completed
Iteration #3
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary